## Agile Project Plan Template
Pembelajaran Mesin | Deteksi Polusi Mikroplastik Melalui Deep Learning Dengan CNN HyperTuning | [7 empty] | Gantt Chart
TOTAL TASKS | 5 |  | DURATION | 71 |  | Overall Progress
Completed | 5 |  | START | 2022-10-05
In progress | 0 |  | FINISH | 2022-12-14 |  | 99%
Not Started | 0
1%
SPRINT | TASKS | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION | STATUS | REMARKS
project implementasi deep learning | Dataset management | Aria |  | 2022-10-05 | 2022-10-06 | 2 | Completed
| Data preprocessing | Rivaldi |  | 2022-10-25 | 2022-10-25 | 1 | Completed
| Architecture Modelling | Aria |  | 2022-10-26 | 2022-10-27 | 2 | Completed
| Evaluation Model | Rivaldi |  | 2022-10-31 | 2022-12-14 | 45 | Completed
| Testing Model | Aria |  | 2022-11-02 | 2022-12-14 | 43 | Completed